GUIDELINES

Title:			ITSC Production Acceptance Criteria

Project Identification

| Project Name |  |
| --- | --- |
| RFC Number and title |  |
| Sponsoring Organisation Unit |  |
| Project Executive |  |
| Senior Supplier(s) |  |
| Senior User(s) |  |
| Project Manager |  |

Approvals

Approval for acceptance of the change to transition into production is provided by a number of stakeholders, each of whom provides sign-off for their specific area of control and responsibility.

Approvals will be obtained by the Project Manager or Change Owner, with evidence of sign-off captured in this document. Once all approvals have been obtained, the document is to be attached to the RFC’s record and submitted by the Project Manager or Change Owner to the Change Advisory Board (CAB) to support the CAB’s decision for approving the implementation of the change.

| Role | Sign Off | Date | Comment |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Project Executive |  |  |  |
| CIO (only required if there are conditions or risks noted in any of the criteria) |  |  |  |

Table of Contents

1	Intent	2

2	Organisational Scope	2

3	Definitions	3

4	ITSC Acceptance Criteria sign off	4

4.1	Criteria for Architectural Considerations and Compliance	5

4.2	Criteria for Information Security, Risk and Compliance	6

4.3	Criteria for IT Service Management Acceptance	8

4.4	Criteria for Operational Acceptance	10

4.5	Criteria for Ongoing Support Acceptance	13

4.6	Criteria for Business Acceptance	14

# Intent

The Production Acceptance Criteria is in place to protect the production environment when introducing change. It ensures that Project Managers and Change Owners are aware of the criteria required to be met when transitioning a change into the production environment.

The Production Acceptance Criteria can be seen as a tool for projects and other changes which identifies the deliverables that are required to support the successful transition of the change into production; specifically, in terms of effective establishment and support of the ongoing operational environment to support the change.

# Organisational Scope

The completion of the Production Acceptance Criteria will be required for the following changes:

- All IT projects

- The introduction of any new IT Service; be this a new application or through the provision of other Service capabilities

- Major enhancement to an existing IT Service which results in a change to how the IT Service is managed when in normal operations i.e. an existing IT Service has been changed to such an extent that its implementation needs to be viewed in the same way as the introduction of a new IT Service.

- Refreshes to the IT infrastructure components that make up an IT Service.

- Major version upgrades of key application software.

ITSC Program Management Office (PMO) issues this document as a template. It is provided to the Project Manager on initiation of a project. The Production Acceptance Criteria must be planned in at the project initiation stage and not used solely as a checklist at the end of the project.

For non-project changes that require Production Acceptance Criteria the document is used as a planning tool during the lifecycle of the change.

# Definitions

| Business Continuity Plan (BCP) | A clearly defined and documented plan for use at the time of an event/incident and/or crisis that disrupts the business operations. Typically a plan will cover all the key personnel, resources, services and actions required to manage the incident through to resolution and restoration of normal business operations. |
| --- | --- |
| Business System Owner | The senior executive of the enterprise unit responsible and accountable for the system. |
| Change Advisory Board (CAB) | The body established under the Change and Configuration process to review and approve changes to production systems. |
| Change Management Process | The documented process for managing changes in production applications and supporting technical infrastructure. Each application must have a documented process setting out how changes are to be managed and approved. |
| ICT Policy | Formal Information and Communication Policy. |
| ICT Security Guidelines | Guidelines supporting the ICT Policy covering ICT security. |
| IT Service | A Service provided to one or more Customers, by an IT Service Provider. An IT Service is based on the use of Information Technology and supports the Customer's Business Process. |
| Project Board | The group representing the interests of the enterprise including users and suppliers and provides overall direction and management of the project. The Board is chaired by the Project Executive, the senior executive with ultimate accountability for the success of the project (also known as the project sponsor) The role of the Project Executive may be delegated as deemed appropriate by the senior executive. |
| RFC | Request For Change. A formal proposal to implement the Project into production. RFC record is raised in ServiceNow and contains details of the proposed change. |
| Service Catalogue | The Service Catalogue is a module of ServiceNow. It contains request-able items and services. All ECU staff can access the Service Catalogue via a web interface called the IT Services Kiosk. |
| ServiceNow | ServiceNow is a Service Management Tool built around the ITIL framework. ECU uses Software as a Service (SaaS)-based offering and currently has the following modules in place: Request, Incident, Problem, Change and Service Catalogue. |
| User Acceptance Testing (UAT) | Is an independent test developed, planned and performed by users prior to accepting the delivered system. It focuses on the business fit of the system to the organisation, rather than technical issues. |
| Vulnerability Testing | Using tools and processes to ensure that the security implementation actually provides the protection that the organisation requires and expects. |

# ITSC Acceptance Criteria sign off

As part of the formal process to transition from development into production ITSC must be satisfied that IT and the business requirements are appropriately addressed. It is not the intention that all questions must have a positive response. Where a question has a negative response, an explanation must be provided that explains the reason why the response has been framed the way it has. Each question needs to be addressed, considered and a response provided in the context of the change under consideration.

Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation, specifying document name and location.

Individual criteria listed in the body of the document can be signed off at various stages of the project. The guide is provided for each of them. This example is for the Criteria for Architectural Considerations and Compliance. It shows that the Architects team needs to be consulted (C) during these project stages: Concept, Business case, Start-up, Design, Procure and Build and the final sign off (S) takes place at the Transition stage of the project.

Project stages

| Concept | Business Case | Start-up | Design | Procure | Build | Test | Transition | Post transition |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C | C | C | C | C | C |  | S |  |

C = consulted, S = final sign off

The final sign-off is located on page 1 of the document and should be signed by designated people after the individual criteria are signed.

## Criteria for Architectural Considerations and Compliance

| No. | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| Architectural considerations and Compliance | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; C; C; C; C; C; S. C = consulted, S = final sign off Architectural Compliance The change must be assessed against endorsed Strategies, Architectural Principles and Recommendations. Operational Initiatives / Changes: Must conduct a self-assessment against the “Operational Change Architecture Impact Checklist”. - Where all checklist criteria have been assessed and none apply the initiative may proceed without engagement of the ECU Architecture team. - Where one or more of the checklist criteria do apply. The Architecture Team must be engaged during initiative commencement to determine the necessary involvement and formalise the required PAC requirements. Project Changes: Must engage with the Architecture team in accordance with the Solution Architecture Framework. PAC sign-off will require achievement of the “As-Built” architectural checkpoint, demonstrated through formal approval captured in either the; - Solution Architecture & Design deliverable, or - Technical Detailed Design deliverable. As a minimum. all changes must produce / update (if existing), a; - Technical & Business, Fit & Value Assessment. - Logical Information Flow Model. - Physical Technology Model. - Physical Application Model. All architectural deliverables must be produced in iServer, in accordance with the established Solution Architecture Toolkit and have fully populated meta-data. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Architecture Services Lead Architect |
|  |  |  |  |  | …………………… Signature and date |

## Criteria for Information Security, Risk and Compliance

| No. | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| InfoSec Consideration and Compliance | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; C; C; C; C; S. C = consulted, S = final sign off Information Security Compliance The change must be assessed against InfoSec Framework. Assessment takes place during 6 project phases to ensure the following principles are embedded in the information system. - Privacy by default - Information & ICT security by-design - Business & ICT Continuity by-design - Risk are identified, analyzed and accepted or mitigated by business and IT management. Change Owner must conduct an assessment against the Operational Change InfoSec Checklist: https://wiki.it.ecu.edu.au/pages/viewpage.action?pageId=46992390 After all checklist criteria have been assessed: - Sign the InfoSec Checklist - Provide a signed copy or its location to the InfoSec team. The InfoSec team must be engaged to determine the necessary involvement and formalize PAC requirements. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Information Security, Risk and Compliance InfoSec Analyst |
|  |  |  |  |  | …………………… Signature and date |
| Software Licensing | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; C; S. C = consulted, S = final sign off The appropriate software licenses have been purchased including the first year of annual support and maintenance. Ongoing costs needed to fund the license maintenance past the first year including provision for any future license growth, have been calculated and included in future budget planning documentation to assist the ongoing financial management of software licensing. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Information Security, Risk and Compliance Manager, Compliance |
|  |  |  |  |  | …………………… Signature and date |
| DR/Failover | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off The Business System Owner and ITSC have agreed to the Tier assigned and the associated RTO and RPO have been documented in Service Now. The servers that support this Business Service have been enabled for Failover (only applies to ECU Tiers 0, 1 and 2). - A System Recovery Test has been requested through the IT Services Kiosk (https://edithcowan.service-now.com/kiosk/services_for_the_itsc.do) - System Recovery Testing (where possible) has been completed successfully - This will evaluate the ability to recover data from failures leading to the loss or corruption of data; and ability to restore from the last known backup. Note: The ATOS team manages the backup system. - System Recovery and Business Support Services Documentation covering this Service exists - The evidence for acceptance will be a completed System Recovery Test Plan from the Senior Recovery Advisor. System Recovery Documentation can be found here: https://wiki.it.ecu.edu.au/display/sysrec/System+Recovery Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No | Agreed Tier ________ | Information Security, Risk and Compliance Senior Recovery Adviser |
|  |  |  |  |  | …………………… Signature and date |

## Criteria for IT Service Management Acceptance

| No. | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| UAT | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off User acceptance testing (UAT) has been completed and the Senior User/Project Executive has signed off on performance. All outstanding failed UAT or Systems tests are added to Problem Management with an appropriate workaround. New or enhanced IT Services must be accepted by the business through formalized UAT in a controlled test environment (normally QA) prior to being implemented into production. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |
| TSR | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off The ITSC Technical Services Register (TSR) has been updated with; - New or enhanced IT Service, - Business System Owner The following fields are mandatory for any upgrades: - Current/Installed Version - Last Upgrade Date - Vendor Mandated Minimum Patch/Upgrade Schedule - Current ECU Patch/Upgrade Schedule ITSC Technical Services Register (TSR) location: https://apps.ecu.edu.au/itsc/technical-service-register/login.php Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Infrastructure Manager |
|  |  |  |  |  | …………………… Signature and date |
|  |  |  |  |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |
| Service Management Considerations | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C1; S1/C2; S2. C = consulted, S = final sign off Consult 1: Define the service SLA’s and Tier. (Mandatory to proceed with design phase) Based on Tier to Service Availability Design Considerations: https://trim-app-p2.ads.ecu.edu.au/HPRMWebClient/HPRMServiceApi/Record/1444288/File/Document Sign 1 /Consult 2: - Confirm that the SLA requirements have been included for the design phase. Date and initial. - Identify impacts to IT processes, internal communications, ITSC webpages and ServiceNow. This includes changes or additions to the Catalogue, CI’s, Knowledge Base Items and or Portal configurations. 2 Sign: - ServiceNow Technical Service CI’s created or updated. - Appropriate ServiceNow KB items created or updated. - Appropriate Catalogue items/ Portal configurations / ITSC Websites created or amended. - Appropriate IT processes created or amended. - Confirm that SLA’s recorded appropriately for the service Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Service Management Senior Service Analyst |
|  |  |  |  |  | ………………… Signature and date |
|  |  |  |  |  | …………………… Signature and date |

## Criteria for Operational Acceptance

| No. | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| Technical Environments - Dev, QA, PROD | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off Environments have been built and tested to enable the ongoing support and development of the Service. Where an environment has not been built, specific approval for this decision shall be provided. State environments to be provided: DEV; ☐. QA; ☐. PROD; ☐. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Infrastructure Manager |
|  |  |  |  |  | …………………… Signature and date |
| Storage | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off Data storage requirements have been assessed with respect to future growth. Future growth estimates have been documented in the system documentation. This should take into consideration all environments built i.e. Development, QA and Production. Applications and Infrastructure teams take accountability for capacity planning. Where the project’s implementation will see increased storage requirements, the project will need to fund these storage requirements for the first 3 years. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Infrastructure Manager |
| MOE | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; C; C; S. C = consulted, S = final sign off The Product (Installable Client Software) OR Web Application OR Software as a Service (SaaS) has been tested against a current generation SOE computer or endpoint before release. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Services Management Software Fleet Manager |
|  |  |  |  |  | …………………… Signature and date |
|  |  |  |  |  | …………………… Signature and date |
| Systems Monitoring | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off Agreed system monitoring has been configured. Systems are monitored with WhatsUp Gold BPS staff can assist with configuring this monitoring. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Business Systems Services Manager, Business Process Services |
|  |  |  |  |  | …………………… Signature and date |
| Performance Testing | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; S. C = consulted, S = final sign off Performance Testing conducted to evaluate the requirements of a system to agreed performance criteria e.g. expected response times met. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | 0, 1 & 2 | Yes / No |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |
| Load Testing | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; S. C = consulted, S = final sign off Appropriate load testing has been performed and the system design is appropriate for the load expected, including future growth. The BSS & Operations teams can assist with load generation and test design. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | 0, 1 & 2 | Yes / No |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |
| Elevated access removed | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off To ensure that the application can run without elevated access should it need an account to run, the Tech Lead or Vendor needs to confirm they can perform the majority of BAU i.e. stop and start services etc. without an elevated account. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |
| Data Warehouse | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; C; S. C = consulted, S = final sign off Impact on Data Warehouse have been assessed and addressed. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | 0, 1 & 2 | Yes / No |  | Business Systems Services Manager, Data Warehouse |
|  |  |  |  |  | …………………… Signature and date |

## Criteria for Ongoing Support Acceptance

| No | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| ITSC Operational Handover | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. C; S. C = consulted, S = final sign off Handover to the ongoing support teams in ITSC has been completed. Ensure that each support level within ITSC has been provided with the necessary information to enable the smooth and effective transition of the change into production and its ongoing support. - 1st Level Support (IT Service Desk) - 2nd Level Support (IT Campus Teams – Customer Support Officers) - 3rd Level Support (Specialist support within the various ITSC teams. Where support involves a 3rd party vendor, the online support contact information form available on the Wiki is required to be completed. https://wiki.it.ecu.edu.au/display/uc/Home Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Services Management Manager, Customer Support |
|  |  |  |  |  | …………………… Signature and date |
|  |  |  |  |  | Business Systems Services Business Process Services Manager, Business Process Services |
|  |  |  |  |  | …………………… Signature and date |
|  |  |  |  |  | Business Systems Services Principal Systems Analyst |
|  |  |  |  |  | …………………… Signature and date |

## Criteria for Business Acceptance

| No | Acceptance Criteria | Applies to Tier | Response | Comment (Mandatory if answering ‘No’) | Confirmed by |
| --- | --- | --- | --- | --- | --- |
| BCP | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off Business Continuity Plan (BCP) is in place to be used in situations where the IT system is unavailable for whatever reason. The Business System Owner must ensure that appropriate business continuity processes are in place in case this system fails. ITSC Technical Services staff can help to determine what recovery time and point objectives are achievable based on System Recovery Testing. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Business System Owner |
|  |  |  |  |  | …………………… Signature and date |
| Business Readiness | Project stages Concept; Business Case; Start-up; Design; Procure; Build; Test; Transition; Post transition. S. C = consulted, S = final sign off Schools and Centres that will be impacted by the Change are suitably prepared to accept the Change by ensuring that all aspects of people, processes, tools and partners have been considered. This ensures that projects have considered, planned, engaged, communicated and delivered to the business areas all aspects of the new or enhanced IT Service that will impact them as part of its transition and ongoing use. Evidence that the criteria have been addressed need to be provided in the form of references to the supporting documentation specifying document name and location: | All | Yes / No |  | Business System Owner |
|  |  |  |  |  | …………………… Signature and date |